## SIQ
SIQ_ID | Questions | Answer | Status | Comments | Who asked | who answered | Date Asked | Due Date
SIQ_1 | What are the displayed modes | There are 4 modes current temp temp adjust fan adjust temp and fan displayed | Satisfied | No we said that there will be only 3 modes: 1-temp and fan displayed 2-temp adjust 3-fan adjust | Youssef Medhat | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_2 | Does Push button change Its behaviour in case of long press | No It doesn't change Its behaviour in case of long or short press | Satisfied | Accepted | Youssef Medhat | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_3 | What is the expected behaviour if 2 buttons clicked together? | It shouldn't do anything | Satisfied | At same time so nothing happen | Sara Safwat | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_4 | What should screen display when It used for the first time? | It should display the minimum temp (16) and fan level (low). | Satisfied | Accepted Temprature at first line and Fan Speed at second line | Hadeel Yamni | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_5 | What is meant by 5 seconds delay at start and end? | System should take 5 seconds delay when on or off button clicked | Satisfied | Accepted | Hadeel Yamni | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_6 | What is the type of connection used ? IR Or wired? | Wired connection | Satisfied | Accepted | Youssef Medhat | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_7 | Fan speed ranges? | Low Medium High | Satisfied | Accepted | Hadeel Yamni. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_8 | Default Fan speed? | Low | Satisfied | Accepted | Hadeel Yamni. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_9 | Default temp ? | 16 | Satisfied | Accepted | Hadeel Yamni. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_10 | Temp range? | 16-32 | Satisfied | Accepted | Youssef Medhat. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_11 | Type of power used? | 9v Battery | Satisfied | Accepted | Enas Taher. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_12 | Any indicator displayed in the LCD? | Yes, something like this > | Satisfied | Not something like this. An Indicator should be appear at the current editable line | Youssef Medhat. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_13 | LCD Size | 2x16 | Satisfied | Accepted | Hadeel Yamni. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_14 | Type of Microcontroller used? | Any. | Satisfied | Accepted | Abdullah Fathy. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_15 | Type of button used? | Ordinary Push Button. | Satisfied | Accepted | Abdullah Fathy. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_16 | what does the "mode button" do? | there are 3 modes 1/adjust temp which mean that cursor on temp line 2/adjust fan which mean that ceruse on fan line 3/display y mode which just display temp and fan level without cursor | Satisfied | Accepted | Youssef Medhat. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_17 | Dose any button make sound when we press it?/ Should system make any notification when any button clicked? | 1/on&off button make a sound (buzzer) 2/up%down make different sound(buzzer) | Satisfied | Only mode have different sound Don't forget Increase and Decrease buttons | Enas Taher. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_18 | Should the any button if pressed for longer period make adiffrent sound? | No, it should make the regular sound one to each press. | Satisfied | Accepted | Enas Taher. | Islam Yasser | 2018-03-31 | 2018-04-01
SIQ_19 | When i press off button, does the screen still show the las temp and the fan level, or should it power off? |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-01
SIQ_20 | What should happen to the Display mode (Temp and fan level) when i press on button which is already on? show the default temp and fan or show the last ? |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-01
SIQ_21 | When i increase or decrease the temp or fan level, Is it appear alone in the different screen or it's apear in the same screen next to the temp line |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-04
SIQ_22 | After changing the temp,, should it be in the menu or go back to the display screen |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-04
SIQ_23 | When i press ON button when it's already ON |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-04
SIQ_24 | What happen when i press UP/DOWN button in the display screen |  | Waiting to an answer |  | Yasmeen Yahia |  | 2018-04-05
SIQ_25 | what shall buzzer do at clicking on button | producing tick sound for 5 seconds | Satisfied |  | Youssef Medhat |  | 2018-04-14
SIQ_26 | what shall any other button do after clicking ? | producing beb sound once | Satisfied |  | Youssef Medhat |  | 2019-04-14

## Sheet2
Satisfied
Unsatisfied
Waiting to an answer