## Sheet1
Project Name:Air conditioner remote controller
Indicators | Probability | Impact |  | Response type
| 5> 75% | 5= Critical |  | Avoid
| 4> 50% | 4= Severe |  | Transfer
| 3> 25% | 3= Major |  | Mitigate
| 2> 10% | 2= Moderate |  | Accept
| 1> 0 % | 1= Minor
ID | Risk | Risk Description | Probaility | Impact | Priority score
1-Communication
1.1 | Project team misunderstand requirements | When requirements are misinterpreted by the project team a gap develops between expectations, requirements and work packages. | 4 | 5 | 20
1.2 | Communication overhead | When key project resources spend a high percentage of their time engaging stakeholders on project issues and change requests their work may fall behind. | 2 | 3 | 6
1.3 | Under communication | Communication is a challenge that's not to be underestimated. You may need to communicate the same idea many times in different ways before people remember it. | 3 | 4 | 12
1.4 | Users have inaccurate expectations | The risk that users believe the project is building an apple when you're really building an orange (i.e. users don't understand the product that's coming their way). | 4 | 3 | 12
1.5 | Impacted individuals aren't kept informed | A stakeholder is missing in your communication plan. Anyone who isn't informed but is impacted has an excellent reason to throw up project roadblocks. For example, if you build a system but fail to consult the operations group that will be responsible for support. | 3 | 3 | 9
2-Resources & Team
2.1 | Resource shortfalls | Inability to secure sufficient resources for the project. | 2 | 4 | 8
2.2 | Learning curves lead to delays and cost overrun | When your project team need to acquire new skills for the project there's a risk that productivity will be low. | 2 | 2 | 4
2.3 | Resource performance issues | Resources who perform below expectations. | 3 | 3 | 9
2.4 | Team members with negative attitudes towards the project | Resources who are negative towards the project may actively or passively sabotage project efforts. | 4 | 3 | 12
2.5 | Low team motivation | Your team lacks motivation. This is a particularly common risk for long running projects. | 3 | 3 | 9
2.6 | Lack of commitment from functional managers | These functional managers are important stakeholders whose support is critical. | 2 | 3 | 6
3-Design
3.1 | Design is infeasible | The design isn't possible, is excessively costly or doesn't support the requirements. | 2 | 4 | 8
3.2 | Design lacks flexibility | A poor design makes change requests difficult and costly. | 3 | 3 | 9
3.3 | Design is not fit for purpose | The design is low quality. | 2 | 3 | 6
3.4 | Design fails peer review | It's a good idea to have peers or architectural experts review your designs. | 4 | 2 | 8
4-Technical
4.1 | Technology components aren't fit for purpose | Technology components are low quality. | 2 | 3 | 8
4.2 | Technology components aren't scalable | Components that can't be scaled to meet performance demands. | 4 | 3 | 12
4.3 | Technology components aren't interoperable | Components that lack standard interfaces. | 3 | 4 | 12
4.4 | Technology components lack stability | Components that crash. | 4 | 5 | 20
4.5 | Technology components aren't extensible | Components that are difficult to extend with new capabilities. | 2 | 2 | 4
4.6 | Project management tool problems & issues | Technical problems with the project management tools themselves. | 4 | 3 | 12
5-Integration
5.1 | Integration testing environments aren't available | The risk that environments won't be available to test integration. | 1 | 3 | 3
5.2 | Failure to integrate with business processes | The risk that your product will fail to fit into the existing business. | 1 | 1 | 1
6-Requirements
6.1 | Requirements have compliance issues | If you have any doubt that requirements comply with the law list it as a risk. | 2 | 2 | 4
6.2 | Requirements are ambiguous | Requirements are unclear and open to interpretation. | 5 | 4 | 20
6.3 | Requirements are low quality | Requirements aren't fit for purpose. | 4 | 4 | 12
6.4 | Requirements are incomplete | You can spot obvious holes in the requirements. | 4 | 5 | 20
7-Approvals
7.1 | Delays to stakeholder approvals impact the project | The risk that approval deadlines will be exceeded. | 3 | 3 | 9
7.2 | Business change impacts project | A business innovation changes your industry and impacts the project. | 2 | 3 | 6