## WBS Diagram
WBS OUTLINE & DIAGRAM TEMPLATE
PROJECT TITLE | Digital air conditioning system | COMPANY NAME
PROJECT MANAGER | Mohamed Hassan | DATE | 2018-04-01
Air conditioning system
1 Hardware
1.1
Design
1.2
Selection of Components
1.3 Components Integration
1.1.1
Prototype Hardware Design
1.2.1
Gathering data
1.2.2 Comparision
1.2.3 Components purchasing
1.3.1
Stand-alone Hardware Testing
1.3.2
Integration
2 Software
2.1 Architecture
2.2
Static Design
2.3
Dynamic Design
2.1.1
Overall architecture
2.2.1
Designing DIO module
2.2.2
Designing Timers module
2.2.3
Designing LCD module
2.2.4
Designing Temp module
2.2.5
Designing RTOS module
2.2.6
Designing App layer
2.3.1
Connecting the modules with the app layer
3 Testing
3.1
Unit testing
3.2
Validation
3.1.1 Turn ON/OFF task
3.1.2 Display task
3.1.3 Adjust temp task
3.1.4 Adjust fan speed task
3.1.5 RTOS scheduler
3.2.1
Test Case Execution
3.2.2
Bug Report
3.2.3
System Testing
3.3
UAT
3.3.1
Alpha Testing
3.3.2
Beta Testing

## WBS Outline
WBS OUTLINE & DIAGRAM TEMPLATE
PROJECT TITLE | Digital air conditioning system | COMPANY
PROJECT MANAGER | Mohamed Hassan | DATE | 2018-04-01
PROJECT TITLE
1 | Hardware
1.1 | Design
1.1.1 | Prototype Hardware Design
1.2 | Selection of Components
1.2.1 | Gathering data
1.2.2 | Comparision
1.2.3 | Components purchasing
1.3 | Components Integration
1.3.1 | Stand-alone Hardware Testing
1.3.2 | Integration
2 | Software
2.1 | Architecture
2.1.1 | Overall architecture
2.2 | Static Design
2.2.1 | Designing DIO module
2.2.2 | Designing Timers module
2.2.3 | Designing LCD module
2.2.4 | Designing Temp module
2.2.5 | Designing RTOS module
2.2.6 | Designing App layer
2.3 | Dynamic Design
2.3.1 | Connecting the modules with the app layer
3 | Testing
3.1 | Unit testing
3.1.1 | Turn ON/OFF task
3.1.2 | Display task
3.1.3 | Adjust temp task
3.1.4 | Adjust fan speed task
3.1.5 | RTOS scheduler
3.2 | Validation
3.2.1 | Test case exection
3.2.2 | Bug reports
3.2.3 | System testing
3.3 | UAT
3.3.1 | Alpha Testing
3.3.2 | Beta Testing