## Sheet1
Project Name:
Indicators |  | Probability |  |  | Response type | Impact
|  | 5> 75% |  |  | Avoid | 5= Critical
|  | 4> 50% |  |  | Transfer | 4= Severe
|  | 3> 25% |  |  | Mitigate | 3= Major
|  | 2> 10% |  |  | Accept | 2= Moderate
|  | 1> 0 % |  |  |  | 1= Minor
ID | Risk | Risk Description | Probability | Impact | Priority score
Communication
| Project team misunderstand requirements | When requirements are misinterpreted by the project team a gap develops between expectations, requirements and work packages.
| Communication overhead | When key project resources spend a high percentage of their time engaging stakeholders on project issues and change requests their work may fall behind.
| Under communication | Communication is a challenge that's not to be underestimated. You may need to communicate the same idea many times in different ways before people remember it.
| Users have inaccurate expectations | The risk that users believe the project is building an apple when you're really building an orange (i.e. users don't understand the product that's coming their way).
| Impacted individuals aren't kept informed | A stakeholder is missing in your communication plan. Anyone who isn't informed but is impacted has an excellent reason to throw up project roadblocks. For example, if you build a system but fail to consult the operations group that will be responsible for support.
Resources & Team
| Resource shortfalls | Inability to secure sufficient resources for the project.
| Learning curves lead to delays and cost overrun | When your project team need to acquire new skills for the project there's a risk that productivity will be low.
| Resource performance issues | Resources who perform below expectations.
| Team members with negative attitudes towards the project | Resources who are negative towards the project may actively or passively sabotage project efforts.
| Low team motivation | Your team lacks motivation. This is a particularly common risk for long running projects.
| Lack of commitment from functional managers | These functional managers are important stakeholders whose support is critical.
Design
| Design is infeasible | The design isn't possible, is excessively costly or doesn't support the requirements.
| Design lacks flexibility | A poor design makes change requests difficult and costly.
| Design is not fit for purpose | The design is low quality.
| Design fails peer review | It's a good idea to have peers or architectural experts review your designs.
Technical
| Technology components aren't fit for purpose | Technology components are low quality.
| Technology components aren't scalable | Components that can't be scaled to meet performance demands.
| Technology components aren't interoperable | Components that lack standard interfaces.
| Technology components lack stability | Components that crash.
| Technology components aren't extensible | Components that are difficult to extend with new capabilities.
| Project management tool problems & issues | Technical problems with the project management tools themselves.
Integration
| Integration testing environments aren't available | The risk that environments won't be available to test integration.
| Failure to integrate with business processes | The risk that your product will fail to fit into the existing business.
Requirements
| Requirements have compliance issues | If you have any doubt that requirements comply with the law list it as a risk.
| Requirements are ambiguous | Requirements are unclear and open to interpretation.
| Requirements are low quality | Requirements aren't fit for purpose.
| Requirements are incomplete | You can spot obvious holes in the requirements.
Approvals
| Delays to stakeholder approvals impact the project | The risk that approval deadlines will be exceeded.
| Business change impacts project | A business innovation changes your industry and impacts the project.