## Sheet2
Air Conditioner Screen Review Log
Review ID | Issue Descripton | Source | Status | Owner | Comment | Date
RV_1 | SIQ Missing Questions | SIQ | Opened | Yasmeen Yehia | There are some parts that does not covered in the SIQ | 2018-01-04
RV_2 | SRS Missing Sections | SRS V1.0 | Opened | Hadeel Yamni Sara Safwat | Missing Sections, system features Written scenario in long section without usecase Table of content number is wrong | 2018-04-04
RV_3 | SIQ missing Questions | SIQ | Opened | Yasmeen Yehia | There are some parts that does not covered in the SIQ | 2018-04-04
RV_4 | Testcases Doc. Review | TestCases AirConditioner | Closed | Hadeel Yamni Sara Safwat | Testcases Restructure | 2018-05-04
RV_5 | Test Plan Missing Sections | Test-Plan_1.0 | Opened | Yasmeen Yehia | Missing Sections in items should not be tested and schedule table | 2018-06-04
RV_6 | Configuration Management plan Missing Sections | CM_Plan of Team 4 | Closed | Dina Helmy | Missing Configuration Management tools and Baseline | 2018-06-04