## Sheet2
Air Conditioner Screen Review Log
Review ID | Issue Descripton | Source | Status | Owner | Comment | Date
RV_1 | configuration parameters section is missing | CDD_OS | Opened | Youssef Medhat | there are no configuration parameters added in the document | 20/04/2018
RV_2 | configuration constrains section is missing | CDD_OS | Open | Youssef Medhat | there are no configuration constrains added to the document | 20/04/2018
RV_3 | CDD_Buzzer Missing points in some sections. | CDD_Buzzer | Open | Ismail Samy | In section 3.5 Interface (Services) missing description of last 4 rows which should be filled. | 20/04/2018
RV_4 | CDD_Buzzer Missing points in some sections. | CDD_Buzzer | Open | Ismail Samy | In section 6.2 and 6.3 Configuration Parameters, The comments should be formal not in franko. | 2018-04-20
RV_5 | CDD_Button is Missing point in section 2 | CDD_Button | Opened | Sara Rashwan | Section 2.1.1 miss the "cover" point | 2018-04-20
RV_6 | CDD_Button is Missing two points in section 5 | CDD_Button | Opened | Sara Rashwan | Section 5 is empty | 2018-04-20
RV_7 | CDD_Button history is empty | CDD_Buttton | Closed | Sara Rashwan | section 9 (history) had not been updated | 2018-04-20
RV_8 |  |  | Closed
Closed
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Closed
Closed
Closed
Open
Open
Open
Open
Open
Closed
Closed

## Sheet1
Open
Closed