## Sheet2
Air Conditioner Screen Review Log
Review ID | Issue Descripton | Source | Status | Owner | Comment | Date
RV_1 | SIQ Missing Questions | SIQ | Opened | Yasmeen Yehia | There are some parts that does not covered in the SIQ | 2018-01-04
RV_2 | SRS Missing Sections | SRS V1.0 | Closed | Hadeel Yamni Sara Safwat | Missing functional requirements Section | 2018-04-04
RV_3 | SRS Missing Sections | SRS V1.0 | Closed | Hadeel Yamni Sara Safwat | Written scenario in wrong section | 2018-04-04
RV_4 | SRS Missing Sections | SRS V1.0 | Closed | Hadeel Yamni Sara Safwat | Written scenario without usecases | 2018-04-04
RV_5 | SRS Missing Sections | SRS V1.0 | Opened | Hadeel Yamni Sara Safwat | Table of content number is wrong | 2018-04-04
RV_6 | SIQ missing Questions | SIQ | Opened | Yasmeen Yehia | There are some parts that does not covered in the SIQ | 2018-04-04
RV_7 | Testcases Doc. Review | TestCases AirConditioner | Closed | Hadeel Yamni Sara Safwat | Testcases Restructure | 2018-05-04
RV_8 | Test Plan Missing Sections | Test-Plan_1.0 | Closed | Yasmeen Yehia | Missing Sections in items should not be tested and schedule table | 2018-06-04
RV_9 | Configuration Management plan Missing Sections | CM_Plan of Team 4 | Closed | Dina Helmy | Missing Configuration Management tools and Baseline | 2018-06-04
RV_10 |  | Risk mangment plan | Open | Islam Yasser | Duplicate file as it is found under Schedule and Plans folder | 2018-11-04
RV_11 |  | Screen Shots in Schedule | Open | Islam Yasser | Screen Shots is not clear (Duration has '?') and Conflict (Test case preperation owner is yasmine then she owns review log?) | 2018-11-04
RV_12 |  | Review Log | Open | Islam Yasser | Date colomn is refered to what? | 2018-11-04
RV_13 |  | Review Log | Open | Islam Yasser | Where is the one how solve the issue? | 2018-11-04
RV_14 |  | Review Log | Open | Islam Yasser | Add revision history | 2018-11-04
RV_15 |  | CM_Plan of Team 4 | Open | Islam Yasser | Version History not matched with Version number of the document | 2018-11-04
RV_16 |  | CM_Plan of Team 4 | Open | Islam Yasser | Roles and responsibilty has wiered name (Enje Zinhom) and what is the difference between full access and full authority | 2018-11-04
RV_17 |  | PP_Team4 | Open | Islam Yasser | Risks part not covered in Risk mangment plan? | 2018-11-04
RV_18 |  | RASIC_Table | Open | Islam Yasser | What is the difference between Accountable and Responsible | 2018-11-04
RV_19 |  | RASIC_Table | Open | Islam Yasser | The work not distributed fairly | 2018-11-04
RV_20 |  | Test_Plan | Closed | Islam Yasser | Version: 1.0 Created: 04/04/2018 Last Updated: 04/05/2018 How there is update without new version | 2018-11-04
RV_21 |  | Test_Plan | Closed | Islam Yasser | (MicroController and Hardware Connection) how these items will be tested | 2018-11-04
RV_22 |  | Test_Plan | Closed | Islam Yasser | You must mention the used tools during project | 2018-11-04
RV_23 |  | WBS | Open | Islam Yasser | where is the UAT in testing branch? | 2018-11-04
RV_24 |  | TestCases | Open | Islam Yasser | Where is the objective of TC1 ? | 2018-11-04
RV_25 |  | TestCases | Open | Islam Yasser | Preconditions should be more accurate will be discussed in session | 2018-11-04
RV_26 |  | CM | Open | Islam Yasser | No use for the gitextension and the folders uploaded through web? | 2018-11-04
Rv_27 |  | ACS_SRS V1.2 | Open | Hadeel Yamni | Tabel of content alignment and numbering is wrong. | 04/15/2018
Rv_28 |  | ACS_SRS V1.2 | Closed | Hadeel Yamni | in relevant data is written in introduction section, i.e remove what is written in section introduction 1 | 04/15/2018
Rv_29 |  | ACS_SRS V1.2 | Closed | Hadeel Yamni | update the version of the SRS | 04/15/2018
Rv_30
Rv_31
Rv_32
Rv_33
Rv_34
Rv_35
Rv_36
Rv_37
Rv_38
Rv_39
Rv_40
Rv_41
Rv_42
Rv_43
Rv_44
Rv_45
Rv_46
Rv_47
Rv_48
Rv_49
Rv_50
Rv_51
Rv_52
Rv_53
Rv_54

## Sheet1
Open
Closed